## Slide 1: Project Milestone Progress
Property Acquisition
  615 E. Main St. (Complete)
  Adjacent property for E. Main Access (Complete)
  “Limestone Street” (Complete)
Discuss Project with Stakeholders and consider input / feedback (Complete)
Develop Funding Strategy (Complete)
Secure Contractor and Vendor Bids (Complete)
Construction (In Progress) (The Construction phase to last approximately 12 months)
  The groundbreaking took place on 10/31/22. (Complete)
  Initial site prep and excavation work, water drainage (Complete)
  Foundations (Complete) Framing outside walls (Complete) Front Canopy & Back Patio Roof (Complete)
  Green Metal Roof (Complete) Cement Floor (Complete) Underground Plumbing (Complete)
  Windows & Doors (Complete) Electrical (Complete) Radiant Floor Heating (Complete)
  Siding & Stone Work (Complete) Insulation (Complete) Framing Wall Partitions (Complete)
  Plumbing (Complete) Prime & Paint (Complete) Fire Alarm & Video Surveillance System (In Progress)
  Drywall (Complete) Underground Utilities (Complete) Sidewalks (Complete)
  Driveway & Parking (Complete) Drop Ceiling (Complete) Data & Telephone Services (In Progress)
  Outside Lighting (Complete) Air Conditioning (In Progress) Landscaping (In Progress)
  Back Patio Railings (Complete) Cabinets & Countertops (Complete) Finished Bathrooms (Complete)
  Flooring (Complete) Install desks, chairs, tables (In Progress) Participant Lockers (Complete)
  Appliances (In Progress) Install furniture, TV’s (In Progress) Finish Details (In Progress)
Develop a plan for the 150 Kennedy Street Building (In Progress), Responsibility to the community
Equipment / Materials Purchasing for New Facility
  Initial & Intermediate lists created (Completed) Grants (Completed)
  State licensing applications (In Progress) Occupancy Permit (Completed)
  Community Open House – September 14, 2023, 4:00 PM – 6:00 PM
Updated: 9/8/2023